## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-09-02 | Done | Max 4 hours tasks | Kickoff | Lecture | ILO 2.1 | 1 | 1 | 0
2024-09-02 | Done | Max 4 hours tasks | Learn foundations of AI | Study | ILO 3.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Study%20Content/Artificial%20Intelligence/1.%20Philosophy%20AI%20%26%20Information%20Literacy.pdf
2024-09-02 | Done | Max 4 hours tasks | Learn information literacy | Study | ILO 3.1 | 4 | 3 | -1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Study%20Content/Artificial%20Intelligence/1.%20Philosophy%20AI%20%26%20Information%20Literacy.pdf | Time difference may have been due to me speeding a bit through the information due to it being late in the day.
2024-09-03 | Done | Max 4 hours tasks | Do standup meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-03 | Done | Max 4 hours tasks | Fill in the learning log | Planning | ILO 1.1 | 0.5 | 0.5 | 0
2024-09-03 | Done | Max 4 hours tasks | Research the role of a data scientist | Research | ILO 2.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Study%20Content/Artificial%20Intelligence/2.%20DataLab%201%20Creative%20Brief.pdf
2024-09-03 | Done | Max 4 hours tasks | Watch the 'Minority Report' movie | Research | ILO 3.1 | 2.5 | 3 | 0.5 |  | There were technical difficulties while watching the movie.
2024-09-03 | Done | Max 4 hours tasks | Do research on the roles in a professional data team | Research | ILO 1.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Study%20Content/Artificial%20Intelligence/2.%20DataLab%201%20Creative%20Brief.pdf | For the bronze medal challenge.
2024-09-03 | Done | Max 4 hours tasks | Research AI in/around 'Minority Report' | Research | ILO 3.1 | 1 | 1 | 0
2024-09-04 | Done | Max 4 hours tasks | Learned about the history of AI | Study | ILO 1.1 | 3 | 2 | -1
4&5&6-9-2024 | Done | Max 4 hours tasks | Set up the GitHub page | Study | ILO 2.1 | 3 | 4 | 1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/main | Took a bit longer due to (in my opinion) confusing instructions.
2024-09-05 | Done | Max 4 hours tasks | Finished Jupyter notebook 1 | Study | ILO 0.1 | 3 | 1 | -2 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Jupyter%20Notebooks/2023-24-Y1-BlockA-Python-main/1.%20Variables.ipynb | I have experience with Python so I believe that is why I finished the notebooks so quickly.
2024-09-05 | Done | Max 4 hours tasks | Finished Jupyter notebook 2 | Study | ILO 0.1 | 3 | 1 | -2 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Jupyter%20Notebooks/2023-24-Y1-BlockA-Python-main/2.%20Conditional%20execution.ipynb | See above
2024-09-05 | Done | Max 4 hours tasks | Did the associated tasks with the notebooks | Testing | ILO 0.1 | 1 | 1 | 0
2024-09-06 | Done | Max 4 hours tasks | Do standup meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-06 | Done | Max 4 hours tasks | Follow the Friday Content Review Session | Meeting | ILO 3.1 | 0.5 | 0.75 | 0.25 |  | The session was a bit longer then planned.
2024-09-06 | Done | Max 4 hours tasks | Prepare small presentation | Design | ILO 3.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Block%20A/Dartmouth%20Workshop%20Presentation%20Text.txt | I overestimated the time I needed to make a presentation
2024-09-06 | Done | Max 4 hours tasks | Present | Meeting | ILO 3.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Block%20A/Dartmouth%20Workshop.pptx | Had a few points I could improve on.
2024-09-06 | Done | Max 4 hours tasks | Watch presentations of other students and give feedback | Workshop | ILO 3.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/1c176cf782450a7e11dc8a158a58796e2858d72c/Block%20A/Not%20Proof/FeedbackByMe
2024-09-06 | Done | Max 4 hours tasks | Read Feedback | Study | ILO 3.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/1c176cf782450a7e11dc8a158a58796e2858d72c/Block%20A/FeedbackForMe | Should incorporate this into the ILO 3.1 presentation.
|  |  |  | Total Hours |  | 32 | 27.25 | -4.75
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2024-09-09 | Done | Max 4 hours tasks | Did Algebra 1 math quiz | Study | ILO 0.2 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Mathematics/Algebra%201%20(Week%202%2C%20Monday).pdf | Recap of the basics of middle school, so I easily knew what I needed to do. All mistakes were due to "grammar" mistakes instead of not understanding math.
2024-09-09 | Done | Max 4 hours tasks | Researched chatbots | Research | ILO 2.1 | 4 | 3 | -1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Artificial%20Intelligence/5.%20Intelligent%20Agents%20%26%20Conversational%20AI.pdf
2024-09-10 | Done | Max 4 hours tasks | Datalab I stand-up meeting | Meeting | ILO 1.1 | 0.25 | 0.25 | 0
2024-09-10 | Done | Max 4 hours tasks | Researched information for presentation | Research | ILO 3.1 | 1 | 1 | 0 |  | Preperation for the ILO 3.1 presentation.
2024-09-10 | Done | Max 4 hours tasks | Strategized how to beat the Turing test | Planning | ILO 2.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Artificial%20Intelligence/6.%20DataLab%201%20Creative%20Brief%20%26%20Turing%20Test.pdf | Prepared a strategy for the Turing Test, result is below.
2024-09-10 | Done | Max 4 hours tasks | Did the Turing test | Testing | ILO 2.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Artificial%20Intelligence/6.%20DataLab%201%20Creative%20Brief%20%26%20Turing%20Test.pdf | The Turing test was a bit shorter due to the human responder not needing a ton of time to think.
2024-09-10 | Done | Max 4 hours tasks | Did the 2nd Turing test | Unplanned | ILO 2.1 | 0 | 0.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Artificial%20Intelligence/6.%20DataLab%201%20Creative%20Brief%20%26%20Turing%20Test.pdf | Unplanned game where all guessers were now responders.
2024-09-10 | Done | Max 4 hours tasks | Debated moral & ethical questions around AI | Unplanned | ILO 2.1 | 0 | 0.5 | 0.5 | Nathan and Filip's work logs. | Sudden debate with Nathan and Filip.
10&11-9-2024 | Done | Max 4 hours tasks | Researched AI domains & subdomains | Research | ILO 3.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Artificial%20Intelligence/9.%20Taxonomy%20of%20AI%20II%20%26%20State-of-the-Art%20AI.txt | Is the task for next week Monday but I did it early.
10&11-9-2024 | Done | Max 4 hours tasks | Made inforgraphic regarding AI domains & subdomains | Design | ILO 3.1 | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/783af428b849800147f78fc312a9406b5a83d3d5/Block%20A/9.%20Taxonomy%20of%20AI%20II%20%26%20State-of-the-Art%20AI%202b.png | Is the task for next week Monday but I did it early, took some time due to my program having technical difficulties.
10&11-9-2024 | Done | Max 4 hours tasks | Worked on presentation | Design | ILO 3.1 | 2 | 2 | 0
2024-09-11 | Done | Max 4 hours tasks | Learn the theory of analysing data | Study | ILO 7.1 | 3 | 1.5 | -1.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Artificial%20Intelligence/7.%20Taxonomy%20of%20AI%20I.pdf | Went smoothly. Nothing special.
2024-09-11 | Done | Max 4 hours tasks | Learn how to analyse data | Study | ILO 7.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Study%20Content/Artificial%20Intelligence/7.%20Taxonomy%20of%20AI%20I.pdf | Was more of a slog than above due to motivation dropping.
2024-09-12 | Done | Max 4 hours tasks | Finished Jupyter notebook 3 | Study | ILO 0.1 | 3 | 1 | -2 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Jupyter%20Notebooks/2023-24-Y1-BlockA-Python-main/3.%20Functions.ipynb | Python is going surprisingly easy
2024-09-12 | Done | Max 4 hours tasks | Finished Jupyter notebook 4 | Study | ILO 0.1 | 3 | 1 | -2 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Jupyter%20Notebooks/2023-24-Y1-BlockA-Python-main/4.%20Loops.ipynb | Python is going surprisingly easy
12&13-9-2024 | Done | Max 4 hours tasks | Learn about giving and receiving feedback | Study | ILO 1.1 | 1.5 | 3 | 1.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/73bfc5f2c1234a19df5f18d84af55b4019164afd/Block%20A/Voltooiingscertificaat_Using%20Feedback%20to%20Drive%20Performance.pdf and https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/73bfc5f2c1234a19df5f18d84af55b4019164afd/Study%20Content/Artificial%20Intelligence/8.%20DataLab%202%20Creative%20Brief%20%26%20Feedback.pdf | I did it in parts with big breaks inbetween (stand-up meeting, Friday Content review Session, workshop, lunchbreak) which was not the most efficient way of working
2024-09-13 | Done | Max 4 hours tasks | Datalab II stand-up meeting | Meeting | ILO 1.1 | 0.25 | 0.25 | 0
2024-09-13 | Done | Max 4 hours tasks | Do the workshop in 4.2 | Workshop | ILO 1.1 | 0.75 | 1 | 0.25 |  | Slightly overtime, possibly due to our group being late
2024-09-13 | Done | Max 4 hours tasks | Review the Work and Learning logs | Meeting | ILO 1.1 | 0.33 | 0.33 | 0 |  | They were not sufficient.
2024-09-13 | Done | Max 4 hours tasks | Follow the content review session | Meeting | ILO 3.1 | 0.5 | 0.5 | 0
2024-09-13 | Done | Max 4 hours tasks | Ask about question 18 | Meeting | ILO 0.2 | 0.1 | 0.25 | 0.15 |  | Thought question 18 was solved it was a different way but turns out no, I just did 10=20 somewhere.
2024-09-13 | Done | Max 4 hours tasks | Get interrupted and asked if I'm "Ellis" | Unplanned | ILO 1.1 | 0 | 0.1 | 0.1 |  | Happened.
2024-09-13 | Done | Max 4 hours tasks | Debate with peers | Unplanned | ILO 2.1 | 0 | 0.5 | 0.5 | Nathan and Filip's work logs. | Another sudden debate with Nathan, Filip and Jim.
2024-09-13 | Done | Max 4 hours tasks | Evidence the WorkLog work | Evidencing | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad5854d0c54dc2b5a7182d65a12404889949059b/Block%20A/Worklog%20Y1A%20ADSAI%202024-2025.xlsx | Based on the 1-1 feedback session with the mentor.
2024-09-13 | Done | Max 4 hours tasks | See example of a WorkLog from 2nd-grade student | Unplanned | ILO 3.1 | 0 | 0.1 | 0.1 |  | I saw a real example of how this document should look like. This was an unplanned activity.
2024-09-13 | Done | Max 4 hours tasks | Fill in the learning log for week 2 | Evidencing | ILO 3.1 | 2 | 2 | 0
2024-09-13 | Done | Max 4 hours tasks | Research the topic of facial regonition | Research | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/6b873c86d8d96e9ac32c8d0d9b388c844c4415e4/Block%20A/ILO%203.1%20Sources/Facial%20Recognition
2024-09-13 | Done | Max 4 hours tasks | Work on the presentation that has to be given in a week | Design | ILO 3.1 | 1 | 1 | 0
|  |  |  | Total Hours |  | 35.18 | 31.28 | -3.9
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-09-16 | Done | Max 4 hours tasks | Fill in Work Log | Planning | ILO 1.1 | 0.5 | 0.1 | -0.4 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0a2d6fbbb994fb55e5e426f5a76723a7f2441b9e/Deliverables/Worklog%20Y1A%20ADSAI%202024-2025.xlsx | Went really quick as I already had an idea of what I wanted to do.
2024-09-16 | Done | Max 4 hours tasks | Fill in Learning Log | Planning | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/35cdcd684d815f05e261508f0ab98b67ae74377c/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
16&17-9-2024 | Done | Max 4 hours tasks | Do Algebra 2 Math Exam | Study | ILO 0.2 | 1 | 1.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/1c176cf782450a7e11dc8a158a58796e2858d72c/Study%20Content/Mathematics/Algebra%202%20(Week%203%2C%20Monday).pdf | Had issues with 2 questions.
16&17-9-2024 | Done | Max 4 hours tasks | Work on word document in preperation of presentation | Research | ILO 3.1 | 3 | 6 | 3 |  | Planned to work on it for only one day, ended up working multiple days on it.
16&17-9-2024 | Done | Max 4 hours tasks | Work on ILO 3.1 presentation | Design | ILO 3.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0576af4cf749f03d46a7670764dd6460dbedc51b/Block%20A/Personalized%20Advertisements.pptx
2024-09-17 | Done | Max 4 hours tasks | Do the "a day in the life of a data engineer" | Research | ILO 2.1 | 1 | 0.2 | -0.8 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0a2d6fbbb994fb55e5e426f5a76723a7f2441b9e/Study%20Content/Artificial%20Intelligence/10.%20DataLab%20I%20Creative%20Brief.pdf | Went suprisingly very quick.
2024-09-17 | Done | Max 4 hours tasks | Follow the "Day in the life of" lecture by Oliver Thuong | Lecture | ILO 2.1 | 1 | 1 | 0
2024-09-17 | Done | Max 4 hours tasks | Fill in work log & evidence | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0a2d6fbbb994fb55e5e426f5a76723a7f2441b9e/Deliverables/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-17 | Done | Max 4 hours tasks | Datalab I stand-up meeting | Meeting | ILO 1.1 | 0.25 | 0.25 | 0
2024-09-17 | Done | Max 4 hours tasks | Write script for presentation | Planning | ILO 3.1 | 2 | 0.5 | -1.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0576af4cf749f03d46a7670764dd6460dbedc51b/Block%20A/ILO%203.1%20Presentation%20Script.docx | I thought this would be longer since I thought I wouldn't have plan but it went quickly.
17&19&20-9-2024 | Done | Max 4 hours tasks | Edit script for presentation (based on feedback and practice) | Planning | ILO 3.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/35cdcd684d815f05e261508f0ab98b67ae74377c/Block%20A/ILO%203.1%20Presentation%20Script.docx
17&19&20-9-2024 | Done | Max 4 hours tasks | Practice presentation | Testing | ILO 3.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/35cdcd684d815f05e261508f0ab98b67ae74377c/Block%20A/ILO%203.1%20Presentation%20Script.docx
2024-09-17 | Done | Max 4 hours tasks | Research US banks | Unplanned | ILO 2.1 | 0 | 0.5 | 0.5
2024-09-17 | Done | Max 4 hours tasks | Research Breda International Airport | Unplanned | ILO 2.1 | 0 | 0.5 | 0.5
2024-09-17 | Done | Max 4 hours tasks | Incorporate feedback from peers given in week 1 in presentation | Design | ILO 3.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/1c176cf782450a7e11dc8a158a58796e2858d72c/Block%20A/FeedbackForMe | There was not too much that needed improvement.
2024-09-17 | Done | Max 4 hours tasks | Fill in WorkLog for week 1 | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/35cdcd684d815f05e261508f0ab98b67ae74377c/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-19 | Done | Max 4 hours tasks | Learn introduction to Data Ethics | Study | ILO 3.1 | 4 | 1.25 | -2.75 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/8a67b2098f585c1871e4aa8809119f5341dce29e/Study%20Content/Artificial%20Intelligence/11.%20Risks%20%26%20Benefits%20of%20AI.pdf
2024-09-19 | Done | Max 4 hours tasks | Add refrences to ILO 3.1 presentation | Research | ILO 3.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/35cdcd684d815f05e261508f0ab98b67ae74377c/Deliverables/Task%201%20(Presentation%20on%20AI%20in%20Science%20Fiction)/Personalized%20Advertisements%202.pdf
2024-09-20 | Done | Max 4 hours tasks | Datalab II stand-up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-20 | Done | Max 4 hours tasks | Friday Content Freview Session Week 3 | Meeting | ILO 3.1 | 0.5 | 0.6 | 0.1
2024-09-20 | Done | Max 4 hours tasks | Find and add extra refrences to presentattion | Research | ILO 3.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/35cdcd684d815f05e261508f0ab98b67ae74377c/Deliverables/Task%201%20(Presentation%20on%20AI%20in%20Science%20Fiction)/Personalized%20Advertisements%202.pdf
2024-09-20 | Done | Max 4 hours tasks | Do my presentation | Meeting | ILO 3.1 | 0.1 | 0.1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/92c1dea6ac32f6000bce3a13319deabec641c40c/Deliverables/Task%201%20(Presentation%20on%20AI%20in%20Science%20Fiction)/AI%20in%20SciFic%20Presentation-Maks-Burchard(240894).mp4
2024-09-20 | Done | Max 4 hours tasks | Follow the other peer's presentations | Lecture | ILO 3.1 | 3.9 | 3 | -0.9 |  | The amount of time planned for this by the brightspace documents was too much.
2024-09-20 | Done | Max 4 hours tasks | Filled in Learning Log | Planning | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/35cdcd684d815f05e261508f0ab98b67ae74377c/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-20 | Done | Max 4 hours tasks | Playing chess | Unplanned | ILO 2.1 | 0 | 0.25 | 0.25 |  | Unexpectidly played a game of chess against Filip.
2024-09-20 | Done | Max 4 hours tasks | Evidence the presentation | Evidencing | ILO 3.1 | 0.5 | 0.5 | 0
20&21-9-2024 | Done | Max 4 hours tasks | Finish Jupyter notebook 5 | Study | ILO 0.1 | 3 | 0.75 | -2.25 |  | I think the Python exerecises are going easy because I already have experience with them.
2024-09-21 | Done | Max 4 hours tasks | Finish Jupyter notebook 6 | Study | ILO 0.1 | 3 | 0.75 | -2.25 |  | aI think the Python exerecises are going easy because I already have experience with them.
2024-09-21 | Done | Max 4 hours tasks | Do the codingbat exercises | Study | ILO 0.1 | 1.5 | 1 | -0.5 |  | aI think the Python exerecises are going easy because I already have experience with them.
|  |  |  | Total Hours |  | 34 | 27 | -7
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-09-23 | Done | Max 4 hours tasks | Fill in Learning Log | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/d2b496e88a4ee3c1850650de1206e7613dbd0d85/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-23 | Done | Max 4 hours tasks | Fill in WorkLog | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/d2b496e88a4ee3c1850650de1206e7613dbd0d85/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-23 | Done | Max 4 hours tasks | Watch the Introduction to Data Science kickoff | Research | ILO 10.1 | 1 | 1 | 0
2024-09-23 | Done | Max 4 hours tasks | DataLab preparation | Study | ILO 10.1 | 1 | 0.25 | -0.75 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/d2b496e88a4ee3c1850650de1206e7613dbd0d85/Study%20Content/Data%20Science/Week%204%20Day%201%20(Monday)/240894_MaksBurchard_Week4DataLab1_1.pdf
2024-09-23 | Done | Max 4 hours tasks | Do "What will you be doing for Data Science?" | Research | ILO 10.1 | 0.5 | 0.25 | -0.25
2024-09-23 | Done | Max 4 hours tasks | PowerBI Workshop | Workshop | ILO 10.1 | 4 | 2.75 | -1.25 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/d2b496e88a4ee3c1850650de1206e7613dbd0d85/Block%20A/Introduction%20to%20Data%20Science/certificate.pdf | I have experience working with other Microsoft tools (Word, Excel, Powerpoint, OneNote, Sharepoint) so I had a bit of an instinct as to where things were
2024-09-23 | Cancelled | Max 4 hours tasks | Fill in Learning Log for Week 3 | Planning | ILO 2.1 | 0.5 | 0 | -0.5 |  | I forgot that I did already do it.
2024-09-23 | Done | Max 4 hours tasks | Prepare for the SDG dialogue | Study | ILO 10.1 | 0.25 | 0.25 | 0
2024-09-23 | Cancelled | Max 4 hours tasks | Fill in CRISP-DM | Evidencing | ILO 2.1 | 0.5 | 0 | -0.5 |  | Thought it said I needed to do this but turns out not yet.
2024-09-23 | Done | Max 4 hours tasks | Evidence in the WorkLog | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/32bb9b5a3ab2cc6fe049adc6233d307d3ae5e7bf/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-23 | Done | Max 4 hours tasks | Clean up files in repository | Design | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/commit/d2b496e88a4ee3c1850650de1206e7613dbd0d85
2024-09-24 | Done | Max 4 hours tasks | Fill in WorkLog | Planning | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/32bb9b5a3ab2cc6fe049adc6233d307d3ae5e7bf/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-24 | Done | Max 4 hours tasks | DataLab I stand-up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-24 | Done | Max 4 hours tasks | DataLab preparation review | Meeting | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/7cede706ac94da29bef69c5b2d9a627b11fc84ab/Study%20Content/Data%20Science/Week%204%20Day%202%20(Tuesday)/W4D1%20Feedback.txt
2024-09-24 | Done | Max 4 hours tasks | Defining a Problem Statement | Study | ILO 10.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ba4a7dd5e2410d3ab1e5ab4b7e521cdcbc3e72e1/Study%20Content/Data%20Science/Week%204%20Day%202%20(Tuesday)/DataLab_00_SDG_Indicators%20(3).txt | I did not have a problem with this task so did it quickly.
2024-09-24 | Done | Max 4 hours tasks | Enter feedback into Learning Log | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ba4a7dd5e2410d3ab1e5ab4b7e521cdcbc3e72e1/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-24 | Done | Max 4 hours tasks | Formulating Research Question | Study | ILO 10.1 | 1 | 0.25 | -0.75 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ba4a7dd5e2410d3ab1e5ab4b7e521cdcbc3e72e1/Study%20Content/Data%20Science/Week%204%20Day%202%20(Tuesday)/DataLab_00_SDG_Indicators%20(3).txt | I got the hang of this pretty quickly
2024-09-24 | Done | Max 4 hours tasks | Guest Lecture - Day in Life of | Lecture | ILO 10.1 | 1 | 1 | 0
2024-09-24 | Done | Max 4 hours tasks | SDG Kick-Off Lecture | Lecture | ILO 10.1 | 1 | 1.25 | 0.25 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ce2ea21bdeeb7399b1880dba204ac7fe84a4c498/Study%20Content/Data%20Science/Week%204%20Day%202%20(Tuesday)/SDGs.txt | Took a bit longer than planned.
2024-09-24 | Done | Max 4 hours tasks | Writing an Introduction | Study | ILO 10.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/7cede706ac94da29bef69c5b2d9a627b11fc84ab/Study%20Content/Data%20Science/Week%204%20Day%202%20(Tuesday)/240894_MaksBurchard_DataLab1_1_1.pbix | I already had an idea of what to write so it didn't take too long.
2024-09-24 | Done | Max 4 hours tasks | End of the day reflection | Meeting | ILO 10.1 | 1 | 0.5 | -0.5
2024-09-24 | Done | Max 4 hours tasks | Evidence in the WorkLog | Evidencing | ILO 2.1 | 0.5 | 0.25 | -0.25 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/bf73bb460c64d1b1b17461c3b718e9f5dcef6a2c/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-24 | Done | Max 4 hours tasks | Get a call from the city of Radom | Unplanned | ILO 1.1 | 0 | 0.2 | 0.2
2024-09-24 | Done | Max 4 hours tasks | Reflect in the WorkLog | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/bf73bb460c64d1b1b17461c3b718e9f5dcef6a2c/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-24 | Done | Max 4 hours tasks | Research the SDG's | Research | ILO 10.1 | 0.75 | 0.75 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/ce2ea21bdeeb7399b1880dba204ac7fe84a4c498/Block%20A/Introduction%20to%20Data%20Science/Not%20Proof/SDG%20Info
2024-09-24 | Done | Max 4 hours tasks | Evidence and fill WorkLog | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/724951fe653dc3304798c871afa5990d2938175c/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
24&26-9-2024 | Done | Max 4 hours tasks | Do Algebra 3 Math Exam | Study | ILO 0.2 | 1 | 1.25 | 0.25 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Study%20Content/Mathematics/Algebra%203%20(Week%204%2C%20Monday).pdf | Did it in two parts, which may have contributed to the higher time.
2024-09-24 | Done | Max 4 hours tasks | Search for datasets belonging to the research question | Research | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/c9ac246f0afaff21a70a2e3e201bfdd963252bcc/Block%20A/Introduction%20to%20Data%20Science/SDG%20Data
2024-09-25 | Done | Max 4 hours tasks | Fill in WorkLog | Planning | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-25 | Done | Max 4 hours tasks | Learn introduction to variables | Study | ILO 10.1 | 0.5 | 0.25 | -0.25
2024-09-25 | Done | Max 4 hours tasks | Learn Data Manipulation (Basic Excel features) | Study | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Study%20Content/Data%20Science/Week%204%20Day%203%20(Wednesday)/Basic%20Excel%20Functions.xlsx | I have experience with excel so this wasn't too bad.
2024-09-25 | Done | Max 4 hours tasks | Learn Data Manipulation (Avanced Excel features) | Study | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Study%20Content/Data%20Science/Week%204%20Day%203%20(Wednesday)/Advanced%20Excel%20Functions.xlsx | The instruction were confusing to me but I still managed to keep it in time.
2024-09-25 | Done | Max 4 hours tasks | Watch the Data Sources Video | Workshop | ILO 10.1 | 1 | 0.15 | -0.85
2024-09-25 | Done | Max 4 hours tasks | Follow the Data Transformation Tutorial | Workshop | ILO 10.1 | 4 | 0.5 | -3.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Study%20Content/Data%20Science/Week%204%20Day%203%20(Wednesday)/PowerBI%20Data%20Tutorial.pbix | I have no idea why I was done so fast, I feel like I'm missing something.
2024-09-25 | Done | Max 4 hours tasks | Do the DataLab preparation | Design | ILO 10.1 | 1 | 0.25 | -0.75 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Study%20Content/Data%20Science/Week%204%20Day%203%20(Wednesday)/VariablesDatalabPreparation.pbix | Wasn't much.
2024-09-25 | Done | Max 4 hours tasks | Add the Dashboard to the Learning Log | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-26 | Done | Max 4 hours tasks | Reflect on my mistakes in the Math Quiz | Research | ILO 0.2 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Study%20Content/Mathematics/Algebra%203%20(Week%204%2C%20Monday).txt
2024-09-26 | Done | Max 4 hours tasks | Evidence the WorkLog | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/f095d77286ddaa81169709ebf7fd1239203c1b9f/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-26 | Done | Max 4 hours tasks | Work on the LearningLog | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-26 | Done | Max 4 hours tasks | Check ahead on what we need to do on Friday | Research | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-26 | Done | Max 4 hours tasks | Reflect on tasks in WorkLog | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ad049761820c795bcd83f412384c9fff18011512/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-27 | Done | Max 4 hours tasks | Fill in WorkLog | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a9e3e4dc9bf47b57a0a7f3ec6b55555a6349f814/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-27 | Done | Max 4 hours tasks | DataLab II stand-up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-27 | Done | Max 4 hours tasks | Friday Content Freview Session Week 4 | Meeting | ILO 10.1 | 0.5 | 0.65 | 0.15
2024-09-27 | Done | Max 4 hours tasks | DataLab preparation review | Meeting | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a9e3e4dc9bf47b57a0a7f3ec6b55555a6349f814/Study%20Content/Data%20Science/Week%204%20Day%203%20(Wednesday)/VariablesDatalabPreparation.pbix
2024-09-27 | Done | Max 4 hours tasks | Datacamp Course on EDA | Study | ILO 10.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a9e3e4dc9bf47b57a0a7f3ec6b55555a6349f814/Study%20Content/Data%20Science/Week%204%20Day%205%20(Friday)/Data%20Preparation%20in%20Power%20Bi.pdf
2024-09-27 | Done | Max 4 hours tasks | Evidence the course in WorkLog and Learning Log | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a9e3e4dc9bf47b57a0a7f3ec6b55555a6349f814/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-27 | Done | Max 4 hours tasks | Hands-on Application | Workshop | ILO 10.1 | 3.5 | 2 | -1.5
2024-09-27 | Done | Max 4 hours tasks | End of the day reflection | Meeting | ILO 10.1 | 0.5 | 0.25 | -0.25
2024-09-27 | Done | Max 4 hours tasks | Fill in DataLab preparation review feedback in Learning Log | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/67a89d45d222139e2f0cd51b855a89650717579a/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-27 | Done | Max 4 hours tasks | 1-on-1 mentor meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-27 | Done | Max 4 hours tasks | Fill in mentor meeting feedback in Learning Log | Evidencing | ILO 2.1 | 0.25 | 0.3 | 0.05 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/67a89d45d222139e2f0cd51b855a89650717579a/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-09-27 | Done | Max 4 hours tasks | Evidence tests (Math) with screenshots | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/6594f2f6e6e3fa8d4fa7bbaaa878edf82a7e4891/Study%20Content/Mathematics/Algebra%203%20(Week%204%2C%20Monday).png
2024-09-27 | Done | Max 4 hours tasks | Fill in CRISP-DM | Evidencing | ILO 10.1 | 0.5 | 1 | 0.5 |  | I added more things than I planned to add
2024-09-28 | Delayed | Max 4 hours tasks | Finish Jupyter notebook 7 | Programming | ILO 0.1 | 3 | 0 | -3 |  | I originally had this planned on Thursday but plans got in the way of that, so I did it on Saturday.
2024-09-28 | Delayed | Max 4 hours tasks | Finish Jupyter notebook 8 | Programming | ILO 0.1 | 3 | 0 | -3 |  | See abovea
2024-09-28 | Delayed | Max 4 hours tasks | Do the Codingbat & Hackerrank exercises | Testing | ILO 0.1 | 1.5 | 0 | -1.5 |  | See abovea
2024-09-28 | Done | Max 4 hours tasks | Fill in Learning Log for Week 4 | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/67a89d45d222139e2f0cd51b855a89650717579a/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
|  |  |  | Total Hours |  | 48 | 28.55 | -19.45
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-09-30 | Done | Max 4 hours tasks | Fill in Work Log for Monday | Planning | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-09-30 | Done | Max 4 hours tasks | Fill in Learning Log plans for Week 5 | Planning | ILO 2.1 | 0.25 | 0.25 | 0
2024-09-30 | Done | Max 4 hours tasks | Do the introduction to descriptive statistics | Study | ILO 10.1 | 0.5 | 0.5 | 0
2024-09-30 | Done | Max 4 hours tasks | Hands-on DataCamp course | Workshop | ILO 10.1 | 2 | 3 | 1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Study%20Content/Data%20Science/Week%205%20Day%201%20(Monday)/DataCamp%20course%20-%20Exploratory%20Data%20Analysis%20in%20Power%20BI.pdf | Had a couple problems with the PowerBi not working.
2024-09-30 | Done | Max 4 hours tasks | Introduction to visualisations | Study | ILO 10.1 | 0.5 | 0.5 | 0
30-9 & 01/10-2024 | Done | Max 4 hours tasks | Hands-on application (DataCamp course 2) | Workshop | ILO 10.1 | 2.5 | 2.25 | -0.25 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Study%20Content/Data%20Science/Week%205%20Day%201%20(Monday)/DataCamp%20course%20-%20Data%20Visualization%20in%20Power%20BI.pdf | The DataCamp course crashed while I was doing this, so I finished it on the next day.
30-9 & 01/10-2024 | Done | Max 4 hours tasks | DataLab preparation | Research | ILO 10.1 | 0.5 | 0.5 | 0 |  | Could not finish before DataLab due to above issue.
2024-10-01 | Done | Max 4 hours tasks | Q&A Standup Meeting | Meeting | ILO 10.1 | 0.25 | 0.25 | 0
2024-10-01 | Done | Max 4 hours tasks | DataLab preparation review | Meeting | ILO 10.1 | 0.5 | 0.5 | 0
2024-10-01 | Done | Max 4 hours tasks | EDA on chosen SDG data | Study | ILO 10.1 | 4 | 2.5 | -1.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Block%20A/Introduction%20to%20Data%20Science/Power%20BI%20Progression/SDG_Dashboard_4%20(Testing%20Time).pbix
2024-10-01 | Done | Max 4 hours tasks | End of day reflection | Meeting | ILO 10.1 | 0.5 | 0.5 | 0
2024-10-01 | Done | Max 4 hours tasks | Guest Lecture | Lecture | ILO 10.1 | 1 | 1 | 0
2024-10-01 | Done | Max 4 hours tasks | Add review feedback in Learning Log | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
1&2-10-2024 | Done | Max 4 hours tasks | Learn general data reporting | Study | ILO 10.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Study%20Content/Data%20Science/Week%205%20Day%203%20(Wednesday)/Voltooiingscertificaat_Learning%20Data%20Science%20Tell%20Stories%20With%20Data.pdf
2024-10-02 | Done | Max 4 hours tasks | Data reporting in Power BI | Workshop | ILO 10.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Study%20Content/Data%20Science/Week%205%20Day%203%20(Wednesday)/Achievements%20-%20burchardmaks-9928%20_%20Microsoft%20Learn.pdf | I had a bit of trouble with regards to beginning the Lab section of the course, but managed to pull through in the end.
2&3-10-2024 | Done | Max 4 hours tasks | Advanced data visualizations | Workshop | ILO 10.1 | 1 | 3 | 2 |  | I wanted to do the Microsoft Course as well but didn't have time to do it.
2024-10-02 | Done | Max 4 hours tasks | DataLab Preparation | Study | ILO 10.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Block%20A/Introduction%20to%20Data%20Science/Power%20BI%20Progression/SDG_Dashboard_5%20(W5%20Friday%20I).pbix | I messed up here and accidentally forgot to save the preparation document.
2024-10-03 | Delayed | Max 4 hours tasks | Finish Jupyter notebook 9 | Programming | ILO 0.1 | 3 |  | -3
2024-10-03 | Delayed | Max 4 hours tasks | Finish Jupyter notebook 10 | Programming | ILO 0.1 | 3 |  | -3
2024-10-03 | Delayed | Max 4 hours tasks | Do the Codingbat & Hackerrank exercises | Workshop | ILO 0.1 | 1.5 |  | -1.5
2024-10-04 | Done | Max 4 hours tasks | Plan day in WorkLog | Planning | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-04 | Done | Max 4 hours tasks | DataLab II stand-up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-04 | Done | Max 4 hours tasks | Friday Content Review Session | Meeting | ILO 10.1 | 0.5 | 0.5 | 0
2024-10-04 | Done | Max 4 hours tasks | DataLab preparation review | Meeting | ILO 10.1 | 1 | 1 | 0
2024-10-04 | Done | Max 4 hours tasks | Research questions & subquestions | Research | ILO 10.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Study%20Content/Data%20Science/Week%205%20Day%205%20(Friday)/Questions%20%26%20Subquestions.txt
2024-10-04 | Done | Max 4 hours tasks | Find potential sources for my dashboard | Research | ILO 10.1 | 0.75 | 0.75 | 0
2024-10-04 | Done | Max 4 hours tasks | Do visualizations in PowerBI | Workshop | ILO 10.1 | 2.5 | 2.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Block%20A/Introduction%20to%20Data%20Science/Power%20BI%20Progression/SDG_Dashboard_5%20(W5%20Friday%20III%20(Findings%20II)).pbix
2024-10-04 | Done | Max 4 hours tasks | Fill in CRISP-DM | Evidencing | ILO 10.1 | 0.5 | 0.75 | 0.25 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Study%20Content/Data%20Science/Week%204%20Day%205%20(Friday)/CRISP_DM_Maks_Burchard.docx | I decided to add sources to Zoterro which took up some unexpected time.
2024-10-04 | Done | Max 4 hours tasks | Write down observations based off of visualizations | Research | ILO 10.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/0e8196f7f7e1375f6186a665aa0a8f0317c8e346/Study%20Content/Data%20Science/Week%205%20Day%205%20(Friday)/Observations.txt
2024-10-04 | Done | Max 4 hours tasks | End of day reflection | Meeting | ILO 10.1 | 0.5 | 0.5 | 0
Weekend | Done | Max 4 hours tasks | Check out an example dashboard | Research | ILO 10.1 | 0.25 | 0.25 | 0
Weekend | Done | Max 4 hours tasks | Do math quiz 5 | Study | ILO 0.2 | 1 | 1 | 0
Weekend | Done | Max 4 hours tasks | Use mentor feedback to improve reflections in WorkLog | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0
Weekend | Done | Max 4 hours tasks | Go over earlier weeks in Learning Log and apply the feedback | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0
Weekend | Done | Max 4 hours tasks | Evidence everything in the WorkLog | Evidencing | ILO 2.1 | 1 | 1 | 0
Weekend | Done | Max 4 hours tasks | Figure out why pdfs aren't showing up on pc GitHub | Research | ILO 2.1 | 0.5 | 0.5 | 0
Weekend | Done | Max 4 hours tasks | Check if everything is correct in GitHub | Testing | ILO 2.1 | 1 | 1 | 0
Weekend | Done | Max 4 hours tasks | Fill in Learning Log for week 5 | Evidencing | ILO 2.1 | 1 | 1 | 0
|  |  |  | Total Hours |  | 42.5 | 36.5 | -6
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-10-07 | Done | Max 4 hours tasks | Fill in Work Log for Monday | Planning | ILO 2.1 | 0.5 | 0.5 | 0
2024-10-07 | Done | Max 4 hours tasks | Fill in Learning Log goals for Week 6 | Planning | ILO 2.1 | 0.5 | 0.5 | 0
2024-10-07 | Done | Max 4 hours tasks | Math Quiz 5 | Study | ILO 0.2 | 1 | 1 | 0
2024-10-07 | Done | Max 4 hours tasks | Foundational Concepts of Variability | Study | ILO 7.1 | 1.5 | 0.6 | -0.9 |  | Understood and knew this from my high school days.
2024-10-07 | Done | Max 4 hours tasks | Introduction to Guided Case Study | Workshop | ILO 7.1 | 4 | 3 | -1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a377017cefe7c33797cd29556a6170f1f7e91649/Study%20Content/Data%20Science/Week%206%20Day%201%20(Monday)/certificate.pdf | Finished the DataCamp course quick.
7&8-10-2024 | Done | Max 4 hours tasks | DataLab preparation | Workshop | ILO 7.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a377017cefe7c33797cd29556a6170f1f7e91649/Study%20Content/Data%20Science/Week%206%20Day%202%20(Tuesday)/Variability.txt | Did not finish on Monday, finished on Tuesday.
2024-10-08 | Done | Max 4 hours tasks | Fill in Work Log for Tuesday | Planning | ILO 2.1 | 0.5 | 0.5 | 0
2024-10-08 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-08 | Done | Max 4 hours tasks | DataLab preparation review | Meeting | ILO 10.1 | 0.5 | 1 | 0.5 |  | We discussed the (draft) dashboards in quite some detailes, probably more than was required.
2024-10-08 | Done | Max 4 hours tasks | Add DataLab preparation review feedback to Learning Log | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-08 | Done | Max 4 hours tasks | Presentation Skills Preparation | Study | ILO 10.1 | 4 | 4.5 | 0.5 |  | Extra half an hour probably came from the Storytelling Workshop being an hour shorter.
2024-10-08 | Done | Max 4 hours tasks | Figure out how an inflection point works with the 2nd derivative | Unplanned | ILO 0.2 | 0 | 0.25 | 0.25 |  | Was asked to help figure out why the solution to question 16 of the week 5 math quiz was as it was.
2024-10-08 | Done | Max 4 hours tasks | Storytelling Workshop | Workshop | ILO 10.1 | 2 | 1 | -1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/28077d31e55b3d90e3f96977192ac1ed64eca36d/Study%20Content/Data%20Science/Week%206%20Day%202%20(Tuesday)/Thinking%2C_Fast_and_Slow.pdf | Presenter finished pretty quickly. Evidence is the downloaded Wikpedia page of a book the presenter discussed.
2024-10-08 | Done | Max 4 hours tasks | Write draft description of Dashboard | Research | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/28077d31e55b3d90e3f96977192ac1ed64eca36d/Study%20Content/Data%20Science/Week%206%20Day%202%20(Tuesday)/Dashboard%20Description.txt
2024-10-08 | Done | Max 4 hours tasks | Add column queries changes to Crisp-DM | Evidencing | ILO 7.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/28077d31e55b3d90e3f96977192ac1ed64eca36d/Study%20Content/Data%20Science/Week%204%20Day%205%20(Friday)/CRISP_DM_Maks_Burchard.docx
2024-10-08 | Done | Max 4 hours tasks | Fill in Work Log reflection | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-10 | Done | Max 4 hours tasks | Data Modeling in Datacamp | Workshop | ILO 7.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/41d63ef91a0763ad5105af8caef7f2616f5844bb/Study%20Content/Data%20Science/Week%206%20Day%203%20(Wednesday)/Data%20Modeling%20in%20Power%20Bi%20Certificate.pdf
2024-10-10 | Done | Max 4 hours tasks | DataLab preparation: Correlation | Study | ILO 7.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a653fcda13ee8024a0e56067acbffbc5f93df637/Study%20Content/Data%20Science/Week%206%20Day%203%20(Wednesday)/CorrelationDatalabPreparation.pbix | I was finished pretty quickly with this.
2024-10-11 | Done | Max 4 hours tasks | Fill in Work Log for Friday | Planning | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-11 | Done | Max 4 hours tasks | Stand up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-11 | Done | Max 4 hours tasks | Study a bit of math for exam | Study | ILO 0.2 | 0.75 | 0.75 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/a653fcda13ee8024a0e56067acbffbc5f93df637/Study%20Content/Mathematics/Documents
2024-10-11 | Done | Max 4 hours tasks | Math Exam | Lecture | ILO 0.2 | 2 | 2 | 0
2024-10-11 | Done | Max 4 hours tasks | Math Exam Review | Meeting | ILO 0.2 | 0.1 | 0.1 | 0
2024-10-11 | Done | Max 4 hours tasks | DataLab preparation review | Meeting | ILO 7.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a653fcda13ee8024a0e56067acbffbc5f93df637/Study%20Content/Data%20Science/Week%206%20Day%205%20(Friday)/Considerations.txt
2024-10-11 | Done | Max 4 hours tasks | Friday Content Review Session | Meeting | ILO 7.1 | 0.5 | 0.5 | 0
2024-10-11 | Done | Max 4 hours tasks | Recommendations for Future Analyses | Research | ILO 7.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a653fcda13ee8024a0e56067acbffbc5f93df637/Study%20Content/Data%20Science/Week%206%20Day%205%20(Friday)/Recommendations%20for%20Future%20Analyses%20%26%20Data-driven%20Decisions.txt
2024-10-11 | Done | Max 4 hours tasks | Search up sources for Bronze Medal Challange | Research | ILO 2.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/a653fcda13ee8024a0e56067acbffbc5f93df637/Block%20A/Medal%20Challenges/Bronze/Sources
2024-10-11 | Cancelled | Max 4 hours tasks | In-Class discussion | Meeting | ILO 7.1 | 1 | 0 | -1 |  | Did not happen
2024-10-11 | Done | Max 4 hours tasks | Make preparations for Bronze Medal Challange | Design | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a653fcda13ee8024a0e56067acbffbc5f93df637/Block%20A/Medal%20Challenges/Bronze/DS%20Team%20Roles.txt
2024-10-11 | Done | Max 4 hours tasks | Evidence the WorkLog | Evidencing | ILO 2.1 | 1 | 1 | 0
2024-10-11 | Done | Max 4 hours tasks | Evidence and fill in the Learning Log | Evidencing | ILO 2.1 | 1 | 1 | 0
|  |  |  | Total Hours |  | 33.6 | 30.45 | -3.15
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-10-14 | Done | Max 4 hours tasks | Fill in Work Log (Monday) | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/9b2f2eb9beebbdd1eee69c22ba58e1e5d4ef679a/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-10-14 | Done | Max 4 hours tasks | Fill in Learning Log plans (Week 7) | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/9b2f2eb9beebbdd1eee69c22ba58e1e5d4ef679a/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-10-14 | Done | Max 4 hours tasks | Read the "Differences between Descriptive, Predictive and Explanatory Analyses" paper | Study | ILO 7.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/9b2f2eb9beebbdd1eee69c22ba58e1e5d4ef679a/Study%20Content/Data%20Science/Week%207%20Day%201%20(Monday)/To%20Explain%20or%20to%20Predict%20-%20Galit%20Shmueli.pdf
14&24-10-2024 | Done | Max 4 hours tasks | Do the Introduction to Big Data LinkedIn course | Workshop | ILO 7.1 | 0.5 | 4.16 | 3.66 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/9b2f2eb9beebbdd1eee69c22ba58e1e5d4ef679a/Study%20Content/Data%20Science/Week%207%20Day%201%20(Monday)/Voltooiingscertificaat_Data%20Science%20Foundations%20Fundamentals%202019%20LinkedIn.pdf | During this work was when I suddenly became sick so I was not able to finish this and everything below in the week I was supposed to do it. I also decided to do the entire course instead of just watching the 1 video. 1hr 10 mins so far
2024-10-24 | Done | Max 4 hours tasks | Watch the videos on good & bad predictions | Research | ILO 7.1 | 0.5 | 0.5 | 0
2024-10-24 | Done | Max 4 hours tasks | Do the Reporting best practices DataCamp course | Workshop | ILO 10.1 | 2 | 3 | 1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/9b2f2eb9beebbdd1eee69c22ba58e1e5d4ef679a/Study%20Content/Data%20Science/Week%207%20Day%201%20(Monday)/DataCamp%20Report%20Design%20in%20Power%20BI.pdf | Had a couple problems with the virtual machine in the DataCamp Course, so the course took a bit longer.
2024-10-24 | Done | Max 4 hours tasks | Do the DataLab preparation | Study | ILO 10.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/9b2f2eb9beebbdd1eee69c22ba58e1e5d4ef679a/Deliverables/Task%202-7%20(Dashboard)/CRISP_DM_Maks_Burchard.docx | I had already cited sources in my Crisp-DM document and put them in Zotero, but not in the APA style. So all I had to do was to quickly change them to the correct style.
2024-10-24 | Done | Max 4 hours tasks | Evidence and reflect in the Work Log (Monday) | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a5d9eb9d7577e8315a2835cc99fd7ef3a17bb7cf/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
24&25-10-2024 | Done | Max 4 hours tasks | Write a conclusion (Tuesday) | Research | ILO 10.1 | 3.5 | 4.34 | 0.84 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/5b3620eaad19f32575e3ec4df081e0a077489587/Study%20Content/Data%20Science/Week%207%20Day%201%20(Monday)/Conclusion%20(Tuesday).txt | I had troubles with PowerBI not wanting to calculate things correctly (Pearson Coefficient)
25&26-10-2024 | Done | Max 4 hours tasks | DataCamp Course: User-Oriented Design in Power BI (Wednesday) | Workshop | ILO 10.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/a58d9c678541d8b6146c81875b2150790e270970/Study%20Content/Data%20Science/Week%207%20Day%201%20(Monday)/DataCamp%20User-Oriented%20Deisgn%20in%20Power%20BI.pdf | There was one exercise where the exercise folder wasn't matching up with what the exercise was telling me, which was confusing.
2024-10-25 | Done | Max 4 hours tasks | CCC Hackathon (Week 9 & 10 challenges) | Programming | ILO 0.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/tree/de9e979c13c794ccceb296486ad3026f65d7b2fb/Deliverables/Week%209%20%26%2010%20Challenges/Hackathon
26&27&29-10-2024 | Done | Max 4 hours tasks | Dashboard UX improvements (Wednesday) | Design | ILO 10.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/b4c50b0dbaf98d57a4fd4c21d5ce43acb756d334/Study%20Content/Data%20Science/Week%207/UX%20Improvements%20(Wednesday).txt
26&27-10-2024 | Done | Max 4 hours tasks | Iterating using CRISP-DM (Friday) | Workshop | ILO 10.1 | 4 | 6 | 2 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ff8edd5dee67f1dbf7a8c568572d7ee635093f2c/Study%20Content/Data%20Science/Week%207%20Day%201%20(Monday)/Voltooiingscertificaat_Data%20Science%20for%20Java%20Developers.pdf | Followed the entire course.
2024-10-26 | Done | Max 4 hours tasks | Created Zooniverse acount | Study | ILO 2.1 | 0.1 | 0.1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/ff8edd5dee67f1dbf7a8c568572d7ee635093f2c/Block%20A/Week%209%20%26%2010%20Challenges/Zooniverse/E-mail%20-%20Burchard%2C%20Maks%20(240894)%20-%20Outlook.pdf
26&27-10-2024 | Done | Max 4 hours tasks | Classify images in Zooniverse | Workshop | ILO 2.1 | 4 | 4.3 | 0.3 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/c8fc2141a244e039dad27e2dd568d49e7d1f067e/Study%20Content/Data%20Science/Week%207%20Day%201%20(Monday)/Certificate%20_%20Zooniverse_Maks_Burchard.pdf
2024-10-31 | Done | Max 4 hours tasks | Fill in Learning Log for week 7 | Evidencing | ILO 2.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-10-31 | Done | Max 4 hours tasks | Evidence and reflect in the Work Log for week 7 | Evidencing | ILO 2.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
|  |  |  | Total Hours |  | 32.6 | 39.9 | 7.3
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-10-28 | Done | Max 4 hours tasks | Fill in WorkLog for week 8 | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-10-28 | Done | Max 4 hours tasks | Fill in Learning Log plans for week 8 | Planning | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-10-28 | Done | Max 4 hours tasks | Do Intermediate Data Modeling in Power BI | Workshop | ILO 10.1 | 3 | 4 | 1 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Certificate%20-%20Intermediate%20Data%20Modeling%20in%20Power%20BI.pdf | Had a couple problems with the virtual machine in the course not working. Everntually fixed the problems, but it took some time.
2024-10-28 | Done | Max 4 hours tasks | Do the "Design a semantic model in Power BI" Course | Workshop | ILO 10.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Design%20a%20semantic%20model%20in%20Power%20BI.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Optimize a model for performance in Power BI" Course | Study | ILO 10.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Optimize%20a%20model%20for%20performance%20in%20Power%20BI.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Describe Power BI Desktop models" Course | Study | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Describe%20Power%20BI%20Desktop%20models.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Choose a Power BI model framework" Course | Study | ILO 10.1 | 0.75 | 0.75 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Choose%20a%20Power%20BI%20model%20framework.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Understand scalability in Power BI" Course | Study | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Understand%20scalability%20in%20Power%20BI.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Write DAX formulas for Power BI Desktop models" Course | Study | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Write%20DAX%20formulas%20for%20Power%20BI%20Desktop%20models.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Create and manage scalable Power BI dataflows" Course | Study | ILO 10.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Create%20and%20manage%20scalable%20Power%20BI%20dataflows.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Add measures to Power BI Desktop models" Course | Workshop | ILO 10.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Add%20measures%20to%20Power%20BI%20Desktop%20models.pdf
2024-10-28 | Done | Max 4 hours tasks | Do the "Add calculated tables and columns to Power BI Desktop models" Course | Study | ILO 10.1 | 0.33 | 0.33 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Microsoft%20Learn%20-%20Add%20calculated%20tables%20and%20columns%20to%20Power%20BI%20Desktop%20models.pdf
2024-10-28 | Done | Max 4 hours tasks | Advanced Power BI | Study | ILO 10.1 | 1 | 1 | 0
2024-10-28 | Done | Max 4 hours tasks | Write up ideas on what I need to do on Dashboard | Planning | ILO 7.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/2ae3f576392d9706e6ea6e2210835965cbc6e04f/Study%20Content/Data%20Science/Week%208%20Day%201%20(Monday)/Dashboard%20Improvements.txt
2024-10-28 | Done | Max 4 hours tasks | Evidence and Reflect on Monday in the Work Log | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/aec986e4ddea6178f2607b54e2650c8e1a5bfccf/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-10-29 | Done | Max 4 hours tasks | DataLab stand-up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-10-29 | Done | Max 4 hours tasks | Work on Dashboard | Design | ILO 7.1 | 1 | 3 | 2 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Block%20A/Introduction%20to%20Data%20Science/Power%20BI%20Progression/SDG-Dashboard_15%20(Week%208%20Tuesday%20II).pbix | We had a lot of time to work on our Dashboards.
2024-10-29 | Done | Max 4 hours tasks | Follow peers' presentations | Meeting | ILO 7.1 | 2 | 2 | 0
2024-10-29 | Done | Max 4 hours tasks | Present my own dashboard | Meeting | ILO 7.1 | 0.25 | 0.25 | 0
2024-10-29 | Done | Max 4 hours tasks | Read presentation feedback report | Study | ILO 2.1 | 0.1 | 0.1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Study%20Content/Data%20Science/Week%208%20Day%202%20(Tuesday)/dashboard-feedback-Maks.pdf
2024-10-29 | Done | Max 4 hours tasks | Incorporate feedback from report into dashboard | Design | ILO 7.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Block%20A/Introduction%20to%20Data%20Science/Power%20BI%20Progression/SDG-Dashboard_17%20(Post-Feedback%20II).pbix
2024-10-29 | Done | Max 4 hours tasks | Follow peers' presentations II | Meeting | ILO 7.1 | 2 | 2 | 0
2024-10-29 | Unplanned | Max 4 hours tasks | Help Jim with his presentation | Meeting | ILO 1.1 | 0 | 0.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Study%20Content/Data%20Science/Week%208%20Day%202%20(Tuesday)/dashboard_Jim.pbix | Due to the specifications of Jim's laptop, he could not connect his laptop to the screen, so I helped him by connecting my laptop to the screen and showing his dashboard on my laptop.
2024-10-29 | Unplanned | Max 4 hours tasks | Explain to Jim the Zooniverse week 9&10 challenge | Workshop | ILO 1.1 | 0 | 0.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Block%20A/Week%209%20%26%2010%20Challenges/Zooniverse/Certificate%20_%20Zooniverse_Maks_Burchard_2.pdf | I did this because Jim did not yet do his own research into the challenge.
2024-10-29 | Unplanned | Max 4 hours tasks | Research Hatsune Miku | Research | ILO 2.1 | 0 | 0.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Study%20Content/Data%20Science/Week%208%20Day%202%20(Tuesday)/europe2024_guidebook.pdf | This was to further develop my relationship with my co-students.
2024-10-31 | Done | Max 4 hours tasks | Clean up Work Log | Design | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-10-31 | Done | Max 4 hours tasks | Fill in Learning Log section C | Evidencing | ILO 2.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-10-31 | Done | Max 4 hours tasks | Fill in Self-Assesment Rubric | Evidencing | ILO 1.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/14500c2db919b47ed979ea62a8b6f96f7a9de1e7/Deliverables/Prerequisites/Self%20Assessment%20Rubric%20Y1A%20ADSAI%202024-2025.xlsx
2024-10-31 | Done | Max 4 hours tasks | Finalise Dashboard | Design | ILO 7.1 | 2 | 2.25 | 0.25 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/fc3261285238acafefb698a2011c65aa84a60c4a/Block%20A/Introduction%20to%20Data%20Science/Power%20BI%20Progression/SDG-Dashboard_20%20(Finalisation%20III).pbix | Did a bit more than planned, including colouring the top bar to the NS colours
2024-10-31 | Done | Max 4 hours tasks | Finalise CRISP-DM | Research | ILO 10.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/fc3261285238acafefb698a2011c65aa84a60c4a/Deliverables/Task%202-7%20(Dashboard)/CRISP_DM_Maks_Burchard.docx
2024-10-31 | Cancelled | Max 4 hours tasks | Do the Case Study "Analyzing Job Market Data in Power BI" on DataCamp | Workshop | ILO 10.1 | 3 | 0 | -3 |  | I did not have time to do this as I was too busy working on the final deliverables.
2024-10-31 | Cancelled | Max 4 hours tasks | Do Datacamp Data Analyst Career Track Course | Workshop | ILO 7.1 | 2 | 0 | -2 |  | I did not have time to do this as I was too busy working on the final deliverables.
2024-11-01 | Done | Max 4 hours tasks | Last-minute dashboard changes | Design | ILO 7.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/fc3261285238acafefb698a2011c65aa84a60c4a/Deliverables/Task%202-7%20(Dashboard)/SDG-Dashboard_Final.pbix
2024-11-01 | Done | Max 4 hours tasks | Friday DataLab stand-up meeting | Meeting | ILO 2.1 | 0.25 | 0.25 | 0
2024-11-01 | In-Progress | Max 4 hours tasks | Watch peers' presentations | Meeting | ILO 10.1 | 4 | 3.5 | -0.5 |  | We finished before time.
2024-11-01 | Done | Max 4 hours tasks | Present dashboard | Meeting | ILO 10.1 | 0.15 | 0.15 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/fc3261285238acafefb698a2011c65aa84a60c4a/Deliverables/Task%202-7%20(Dashboard)/SDG-Dashboard_Final.pbix
2024-11-01 | Unplanned | Max 4 hours tasks | Help Jim with presenting his dashboard | Meeting | ILO 1.1 | 0 | 0.15 | 0.15 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/fc3261285238acafefb698a2011c65aa84a60c4a/Study%20Content/Data%20Science/Week%208%20Day%205%20(Friday)/SDGIndicatorsDashboard_JimDucker.pbix | Problems with computer ports, so he used my computer.
2024-11-01 | Done | Max 4 hours tasks | Finalise Self-assesment rubric | Evidencing | ILO 2.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/98f19f8513fc675aaa4f1ea36ed4683bd4c11bc3/Deliverables/Prerequisites/Self%20Assessment%20Rubric%20Y1A%20ADSAI%202024-2025.xlsx
2024-11-01 | Done | Max 4 hours tasks | Finalise Work Log | Evidencing | ILO 2.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/98f19f8513fc675aaa4f1ea36ed4683bd4c11bc3/Deliverables/Prerequisites/Worklog%20Y1A%20ADSAI%202024-2025.xlsx
2024-11-01 | Done | Max 4 hours tasks | Finalise Learning Log | Evidencing | ILO 2.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/98f19f8513fc675aaa4f1ea36ed4683bd4c11bc3/Deliverables/Prerequisites/Learning%20Log%20Y1A%20ADSAI%202024-2025.pptx
2024-11-01 | Unplanned | Max 4 hours tasks | Change CRISP-DM to .pdf format and change the files accordingly | Evidencing | ILO 2.1 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25A-FAI1-ADSAI--MaksBurchard240894/blob/509ef6211152edade770551faf371b9aba8fdc3f/Deliverables/Task%202-7%20(Dashboard)/CRISP_DM_Maks_Burchard.pdf
2024-11-01 | Done | Max 4 hours tasks | Submit the deliverables in Brightspace | Evidencing | ILO 2.1 | 0.1 | 0.1 | 0
|  |  |  | Total Hours |  | 39.68 | 39.08 | -0.6
|  |  |  | Total hours this block |  | 297.56 | 260.01 | -37.55

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 0.1 | 3 | 2 | 2.5 | 0 | 0 | 0 | 4 | 0 | 11.5
ILO 0.2 | 0 | 0.75 | 1.5 | 1.5 | 1 | 4.1 | 0 | 0 | 8.85
ILO 1.1 | 3.5 | 4.93 | 1.35 | 0.2 | 0 | 0 | 0 | 1.65 | 11.63
ILO 2.1 | 6.5 | 6 | 3.7 | 8.55 | 5.5 | 4.25 | 8.4 | 8.6 | 51.5
ILO 3.1 | 14.25 | 13.1 | 17.95 | 0 | 0 | 0 | 0 | 0 | 45.3
ILO 7.1 | 0 | 4.5 | 0 | 0 | 0 | 13.1 | 6.66 | 11.25 | 35.51
ILO 10.1 | 0 | 0 | 0 | 18.3 | 30 | 7 | 20.84 | 17.23 | 93.37
TOTAL HOURS PER WEEK | 27.25 | 31.28 | 27 | 28.55 | 36.5 | 28.45 | 39.9 | 38.73
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
If you add more rows to the Worklog Tasks and Time sheet, make sure to update the row count accordingly. For example, if you add an additional row for Week 1, you'll need to adjust all formula in Column C from H14 to H15 and F14 to F15 | bar: W1 to W4

## Drop-downs (hidden)
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 0.1
Unplanned | Meeting | ILO 0.2
Blocked | Programming | ILO 1.1
In-Progress | Research | ILO 2.1
Done | Testing | ILO 3.1
Delayed | Workshop | ILO 7.1
Cancelled | Planning | ILO 10.1
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break