## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-11-18 | Done | Block B Introduction | Read block B information | Study | ILO 1.2 | 0.5 | 0.5 | 0
2024-11-18 | Done | Block B Introduction | Search for deliverables templates | Research | ILO 1.2 | 0.1 | 0.5 | 0.4 |  | Did not find it because they weren't given to us yet
2024-11-18 | Done | Block B Introduction | Installing Python Packages | Programming | ILO 0.2 | 1 | 1 | 0
2024-11-18 | Done | Packages basics | Learn about Pandas, NumPy and Matplotlib | Study | ILO 0.2 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/NumPy%20user%20guide%20%E2%80%94%20NumPy%20v2.1%20Manual.pdf
2024-11-18 | Done | Packages basics | Watch the "Data Analysis with Python - Full Course for Beginners (Numpy, Pandas, Matplotlib, Seaborn)" video | Study | ILO 0.2 | 4 | 4 | 0
2024-11-18 | Blocked | Packages basics | Do the "Hands-on" exercise | Programming | ILO 0.2 | 1 | 0.5 | -0.5 |  | I could not download "credit.csv"
2024-11-18 | Done | Packages basics | Do the "Hands-on" exercise 2 | Programming | ILO 0.2 | 1 | 1 | 0 |  | I somehow managed to download the file and tried to do the excercises
2024-11-19 | Done | Block B Introduction | Block B Kick-off | Lecture | ILO 1.2 | 1.5 | 1.25 | -0.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Kick_Off_BlockB_Y1_2024_25_ADSAI.pptx
2024-11-19 | Done | Stand-up meeting | Do stand-up meeting with mentor group | Meeting | ILO 2.2 | 0.25 | 0.25 | 0
2024-11-19 | Done | Block B Introduction | Download submission files | Study | ILO 1.2 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/BlockY1B_CreativeBrief.ipynb
2024-11-19 | Done | Fill in WorkLog | Fill in WorkLog for week 1 | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-11-19 | Done | Block B Introduction | Put in GitHub repository on my laptop | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894
2024-11-19 | Done | Block B Introduction | Fill in Learning Log section A | Planning | ILO 2.2 | 0.5 | 0.75 | 0.25 |  | I am not certain what has to be done with the "SMARTER" goals AAA
2024-11-19 | Done | Block B Introduction | Move WorkLog to updated file | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-11-19 | Done | Block B Introduction | Move Python programs to repository for potential future use | Programming | ILO 0.2 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/tree/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Old%20Python%20Files
2024-11-19 | Blocked | Fixing problem | Figure out the GitHub PDF problem | Debugging | ILO 1.2 | 0.5 | 0.5 | 0 |  | For some reason, GitHub refuses to show PDFs on my computer, but on other devices it does work. This is meant to try and fix that. POST-TASK EDIT: Seems to be a problem with GitHub itself and not my device, and there does nto seem to be a solution.
2024-11-19 | Done | Datalab tasks | Do the Tuesday datalab task | Programming | ILO 0.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/W1%20Datalab%20I%20Exercise.txt
2024-11-19 | Done | Block B Introduction | Organize block B and block A files | Evidencing | ILO 1.2 | 0.5 | 0.5 | 0
2024-11-21 | Done | Fill in WorkLog | Fill in WorkLog for Wednesday/Thursday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-11-21 | Done | Read chapter 1 | Introduction and overview | Study | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-21 | Done | Read chapter 1 | What is machine learning? | Study | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-21 | Done | Read chapter 1 | Types of Machine Learning Systems | Study | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-21 | Done | Read chapter 1 | Challenges of Machine Learning | Study | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-21 | Done | Read chapter 1 | Testing, Validating, and Model Selection | Study | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-21 | Done | Read chapter 1 | Complete “ML-quiz-W1” in brightspace | Testing | ILO 8.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/3b3d71a66f4e9950bc4b200f6428d8d3c5793552/Block%20B/2024-11-21.png | I had the content fresh in my mind so I did this quicker than expected.
2024-11-21 | Done | Evidencing | Upload files to GitHub for evidencing | Evidencing | ILO 1.2 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894
2024-11-22 | Done | Fill in WorkLog | Plan in WorkLog for Friday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-11-22 | Done | Stand-up meeting | Stand Up Meeting On Friday With Mentor Group | Meeting | ILO 1.2 | 0.25 | 0.25 | 0
2024-11-22 | Done | Learning SQL | SQL Content review session | Meeting | ILO 8.1 | 1 | 1 | 0
2024-11-22 | Done | Learning SQL | Learn about SQL | Study | ILO 8.1 | 0.5 | 0.5 | 0
2024-11-22 | Done | Learning SQL | Install SQL | Programming | ILO 8.1 | 1 | 1 | 0
2024-11-22 | Blocked | Learning SQL | Figure out how to connect to postgres | Research | ILO 8.1 | 0.5 | 0.5 | 0 |  | Was not able to figure out how to fix the problem.
2024-11-22 | Done | Learning SQL | Re-install PostgreSQL to fix problem | Programming | ILO 8.1 | 1 | 1 | 0
2024-11-22 | Done | Learning SQL | Learn about basic SQL queries | Programming | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-11-22 | Cancelled | Learning SQL | Set up VPN | Programming | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/ADSAI%20Remote%20VPN.pdf | You do not have to do it after finishing the SQL part.
2024-11-22 | Done | Learning SQL | EDA with SQL | Programming | ILO 8.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-11-22 | Done | Fill in WorkLog | Evidence week 1 | Evidencing | ILO 1.2 | 0.5 | 0.5 | 0 |  | AAA
2024-11-22 | Done | Fill in Learning Log | Fill in Learning Log week 1 | Evidencing | ILO 2.2 | 0.5 | 0.5 | 0
2024-11-22 | Done | Fill in Learning Log | Evidence in Learning Log week 1 | Evidencing | ILO 2.2 | 0.5 | 0.15 | -0.35 |  | AAA
|  |  |  | Total Hours |  | 37.35 | 35.9 | -1.45
Week 2
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning] - if any
2024-11-25 | Done | Fill in WorkLog | Fill in WorkLog for Monday | Evidencing | ILO 1.2 | 0.5 | 0.5 | 0 |  | AAA
2024-11-25 | Done | Read chapter 2 | Introduction and Understanding the Problem | Study | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-25 | Done | Read chapter 2 | Data Exploration and Visualization | Study | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-25 | Done | Read chapter 2 | Data Preparation and Feature Engineering | Study | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-25 | Done | Read chapter 2 | Model Selection, Training and Tuning | Study | ILO 8.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-25 | Done | Read chapter 2 | Evaluation, Testing and Deliverables | Study | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-11-25 | Done | Read chapter 2 | Complete “ML-quiz-W2_1” in brightspace | Testing | ILO 8.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/2024-11-25.png
2024-11-26 | Done | Fill in Learning Log | Fill in Learning Log week 2 | Planning | ILO 1.2 | 0.5 | 0.5 | 0 |  | AAA
2024-11-26 | Done | Stand-up meeting | Stand-up meeting Week 2 Datalab 1 | Meeting | ILO 2.2 | 0.25 | 0.25 | 0
2024-11-26 | Done | Packages basics | Re-Install all the Python packages | Programming | ILO 8.1 | 0.5 | 0.5 | 0 |  | For some reason, VSC didn't see the environment I created last week, so I had to go through the process again.
2024-11-26 | Done | Packages basics | Learn MatPlotLib | Study | ILO 8.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Quick%20start%20guide%20%E2%80%94%20Matplotlib%203.9.2%20documentation.pdf
2024-11-26 | Done | Packages basics | Learn Seaborn | Study | ILO 8.1 | 0.5 | 2.35 | 1.85 |  | Unfortunately, during this task the annoucement came in, which threw me off my focus and caused this task to take so long.
2024-11-26 | Done | Packages basics | Install Seaborn for a 3rd time | Programming | ILO 8.1 | 0.1 | 0.1 | 0 |  | Despite installing the package twice already, VSC could not import it.
2024-11-26 | Unplanned | Packages basics | Restart Laptop due to issues | Unplanned | ILO 8.1 | 0 | 0.1 | 0.1 |  | Some features of my laptop were acting up a bit, so I restarted my pc to fix them.
2024-11-26 | Done | Packages basics | EDA with Python | Programming | ILO 8.1 | 4 | 3.55 | -0.45 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-11-27 | Done | Learning Vectors | Learn about Vectors | Study | ILO 8.1 | 3 | 3 | 0
2024-11-27 | Done | Learning Vectors | Search for old Vector materials from High School | Research | ILO 8.1 | 2 | 2 | 0
2024-11-28 | Done | Packages basics | Do the DataCamp course "Exploratory Data Analysis In Python" | Workshop | ILO 8.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/DataCamp%20-%20Exploratory%20Data%20Analysis%20in%20Python.pdf
2024-11-28 | Done | Datalab preparation | Prepare for Friday DataLab | Research | ILO 8.1 | 0.25 | 0.25 | 0
28&29-11-2024 | Done | Datalab Tasks | Analyze the state of Creative Brief Project | Evidencing | ILO 8.1 | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-11-29 | Done | Stand-up meeting | DataLab 2 Stand-up meeting | Meeting | ILO 2.2 | 0.25 | 0.25 | 0
2024-11-29 | Done | Content Review | Friday Content Review Session | Meeting | ILO 8.1 | 0.5 | 0.5 | 0
2024-11-29 | Done | Lecture | Guest Lecture | Lecture | ILO 2.2 | 1 | 0.75 | -0.25
2024-11-29 | Unplanned | Retake application | Attempt to apply for retake of Python Exam | Unplanned | ILO 0.2 | 0 | 0.25 | 0.25
2024-11-29 | Done | Datalab Tasks | EDA with Kaggle dataset | Programming | ILO 8.1 | 4 | 3.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-11-29 | Done | Recieve Feedback | 1-on-1 feedback session with mentor | Meeting | ILO 1.2 | 0.25 | 0.33 | 0.08
2024-11-29 | Done | Fill in Learning Log | Fill in Week 2 Learning Log | Evidencing | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2024-11-29 | Done | Fill in Learning Log | Re-write Learning Log Section A and SMARTER Goals | Planning | ILO 2.2 | 0.5 | 0.5 | 0 |  | I'm still not too sure about the SMATER goals. AAA
2024-11-29 | Done | Fill in Learning Log | Re-write Week 1 and 2 reflection and feedback | Planning | ILO 2.2 | 0.5 | 0.5 | 0 |  | AAA
2024-11-29 | Done | Fill in WorkLog | Evidence week 2 in WorkLog | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-11-29 | Done | Fill in Learning Log | Evidence Week 2 Learning Log | Evidencing | ILO 2.2 | 0.25 | 0.15 | -0.1 |  | AAA
|  |  |  | Total Hours |  | 32.85 | 33.58 | 0.73
Week 3
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-02 | Done | Fill in WorkLog | Fill in WorkLog for Monday | Planning | ILO 1.2 | 0.5 | 0.5 | 0 |  | AAA
2024-12-02 | Done | Fill in Learning Log | Fill in Learning Log Week 3 | Planning | ILO 2.2 | 0.5 | 0.5 | 0 |  | AAA
2024-12-02 | Done | Read Chapter 3 | Read chapter 3 | Study | ILO 8.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-02 | Done | Read Chapter 3 | Read summary of chapter 3 | Study | ILO 8.1 | 0.5 | 0.5 | 0
2024-12-02 | Done | Read Chapter 3 | Complete “ML-quiz-W3_1” in brightspace | Testing | ILO 8.1 | 0.5 | 0.25 | -0.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Quizzes%20-%20Project%201B%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20W3_1.pdf
2024-12-02 | Done | Read Chapter 4 | Read chapter 4 | Study | ILO 8.1 | 4 | 3 | -1 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-02 | Done | Read Chapter 4 | Read summary of chapter 4 | Study | ILO 8.1 | 0.5 | 0.5 | 0
2024-12-02 | Done | Read Chapter 4 | Complete “ML-quiz-W3_2” in brightspace | Testing | ILO 8.1 | 0.5 | 1 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Quizzes%20-%20Project%201B%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20W3_2%202.pdf | Had to help my sister with her school work intermittently while I was doing this quiz.
2024-12-02 | Done | Datalab preparation | Look ahead at the Tuesday DataLab | Research | ILO 8.1 | 0.25 | 0.25 | 0
2024-12-03 | Done | Fill in WorkLog | Fill in WorkLog for Tuesday | Planning | ILO 1.2 | 0.5 | 0.5 | 0 |  | AAA
2024-12-03 | Done | Stand-up meeting | DataLab 1 stand-up meeting | Meeting | ILO 1.2 | 0.25 | 0.25 | 0
2024-12-03 | Done | Datalab Tasks | Implement Linear Regression | Programming | ILO 8.1 | 4 | 5.5 | 1.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb | Took a bit longer than planned.
2024-12-03 | Done | Lecture | Follow the guest lecture | Lecture | ILO 6.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Lead%20Analytics%20%26%20AI%20for%20BUAS.pdf
2024-12-03 | Done | Datalab Tasks | Implement Decision Tree Regression | Programming | ILO 8.1 | 2.5 | 2 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-12-04 | Done | Learning Matrices | Learn about matrices | Study | ILO 8.1 | 4 | 4 | 0
2024-12-04 | Done | Learning Matrices | Application of matrices | Study | ILO 8.1 | 2 | 1 | -1 |  | I was already familiar with amtrices because I learned about them in high school.
2024-12-05 | Done | Read chapter 5 | Introduction to Logistic Regression | Study | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-05 | Done | Read chapter 5 | Training and Cost Function | Study | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-05 | Done | Read chapter 5 | Decision Boundaries | Study | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-05 | Done | Read chapter 5 | Softmax Regression | Study | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-05 | Done | Read chapter 5 | Review the Chapter | Research | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-05 | Done | Read chapter 5 | Complete “ML-quiz-W3_3” in brightspace | Testing | ILO 8.1 | 1 | 1 | 0
2024-12-06 | Done | Stand-up meeting | Stand-up meeting | Meeting | ILO 1.2 | 0.25 | 0.25 | 0
2024-12-06 | Done | Datalab Tasks | Implement regression | Programming | ILO 8.2 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-12-06 | Done | Content Review | Regression Lecture | Lecture | ILO 8.1 | 1 | 1 | 0
2024-12-06 | Done | Datalab Tasks | Work in Creative Brief | Programming | ILO 8.2 | 2.5 | 1.5 | -1 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb | I had done some overlapping work with the previous task so was shorter.
2024-12-06 | Done | Fill in WorkLog | Fill in WorkLog for Friday | Planning | ILO 1.2 | 0.5 | 0.5 | 0 |  | AAA
2024-12-06 | Done | Fill in Learning Log | Fill in Learning Log Week 3 | Planning | ILO 2.2 | 0.5 | 0.5 | 0 |  | AAA
2024-12-06 | Done | Fill in Learning Log | Evidence Learning Log Week 3 | Evidencing | ILO 1.2 | 0.5 | 0.25 | -0.25 |  | AAA
2024-12-06 | Done | Fill in WorkLog | Evidence Work Log Week 3 | Evidencing | ILO 1.2 | 0.5 | 0.25 | -0.25 |  | AAA
|  |  |  | Total Hours |  | 41.25 | 38.5 | -2.75
Week 4
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-09 | Done | Fill in Learning Log | Fill in Learning Log for week 4 | Planning | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-09 | Done | Fill in WorkLog | Fill in WorkLog for Monday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-09 | Done | Read chapter 6 | Training and visualizing decision trees | Study | ILO 8.1 | 1.5 | 1.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-09 | Done | Read chapter 6 | Making predictions and understanding purity | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-09 | Done | Read chapter 6 | The CART training algorithm | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-09 | Done | Read chapter 6 | Regularization Hyperparameters | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-09 | Done | Read chapter 6 | Regression with decision trees | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-09 | Done | Read chapter 6 | Read the chapter 6 summarization | Study | ILO 8.1 | 1 | 1.5 | 0.5
2024-12-09 | Done | Read chapter 6 | Complete “ML-quiz-W4_1” in brightspace | Testing | ILO 8.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Ml-quiz-W4_1%20-%20Results.png
2024-12-10 | Blocked | Datalab Tasks | Implement a classification model | Programming | ILO 8.2 | 4 | 1 | -3 |  | I was sick and was not able to finish it here, I did it later in the week.
2024-12-10 | Done | Datalab Tasks | Practice Notebook | Programming | ILO 8.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Linear-Regression-Co2.ipynb
11&13-12-2024 | Done | Learning Calculus | Learn Calculus | Study | ILO 8.1 | 4 | 3 | -1
2024-12-12 | Done | Read chapter 7 | Introduction to ensemble learning and voting classifiers. | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-12 | Done | Read chapter 7 | Bagging and pasting techniques, along with out-of-bag evaluation. | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-12 | Done | Read chapter 7 | Deep dive into random forests, extra-trees, and feature importance. | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-12 | Done | Read chapter 7 | Boosting techniques, including AdaBoost, gradient boosting, and histogram-based gradient boosting. | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-12 | Done | Read chapter 7 | Stacking Ensembles | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-12 | Done | Read chapter 7 | Read the chapter 7 summarization | Study | ILO 8.1 | 0.5 | 1 | 0.5
2024-12-12 | Done | Read chapter 7 | Complete “ML-quiz-W4_2” in brightspace | Testing | ILO 8.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Quizzes%20-%20Project%201B%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20W4_2.pdf
2024-12-13 | Done | Stand-up meeting | Stand-up meeting | Meeting | ILO 8.1 | 0.25 | 0.25 | 0
2024-12-13 | Done | Datalab Tasks | Start to implement classification model | Programming | ILO 8.2 | 4 | 3 | -1 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb | Had already made a slight start earlier in the week while I was sick
2024-12-13 | Done | Fill in WorkLog | Fill in WorkLog for Friday | Planning | ILO 1.2 | 0.5 | 0.5 | 0 |  | AAA
2024-12-13 | Done | Lecture | Lecture on regression and classification | Lecture | ILO 8.1 | 1 | 1.45 | 0.45
2024-12-13 | Done | Recieve Feedback | 1 on 1 meeting | Meeting | ILO 1.2 | 0.25 | 0.25 | 0
2024-12-14 | Done | Prepare for retake | Prepare for Python retake on Saturday | Programming | ILO 0.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/tree/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20A%20Retakes
2024-12-15 | Done | Prepare for retake | Prepare for Python retake on Sunday | Programming | ILO 0.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/tree/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20A%20Retakes
2024-12-17 | Done | Fill in Learning Log | Add feedback to week 4 Learning Log | Evidencing | ILO 2.2 | 0.5 | 0.5 | 0 |  | AAA
2024-12-17 | Done | Fill in Learning Log | Evidence in Learning Log week 4 | Evidencing | ILO 2.2 | 0.5 | 0.25 | -0.25 |  | AAA
2024-12-17 | Done | Fill in WorkLog | Evidence in WorkLog week 4 | Evidencing | ILO 1.2 | 0.5 | 0.25 | -0.25 |  | AAA
|  |  |  | Total Hours |  | 40.5 | 31.95 | -8.55
Week 5
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2024-12-16 | Done | Fill in WorkLog | Filled in WorkLog planning for Monday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-16 | Done | Fill in Learning Log | Filled in Learning Log for week 5 | Planning | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-16 | Done | Python Retake part 1 | Do the Python Retake | Testing | ILO 0.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20A%20Retakes/New%20folder/Quiz.png
2024-12-16 | Done | Installation | Re-install all programs for Block B on new laptop | Programming | ILO 0.2 | 0.5 | 0.5 | 0
2024-12-16 | Done | Read Chapter 8 | Introduction to dimensionality reduction and understanding the curse of dimensionality. | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Read Chapter 8 | Study of projection techniques, including the PCA method. | Study | ILO 8.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Read Chapter 8 | Deep dive into Random Projection and its applications. | Study | ILO 8.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Read Chapter 8 | Explore manifold learning, focusing on LLE and its benefits. | Study | ILO 8.1 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Review Chapter 8 | Read the Chapter 8 summary | Research | ILO 8.1 | 1 | 1 | 0
2024-12-16 | Done | Review Chapter 8 | Complete “ML-quiz-W5_1” in Brightspace | Testing | ILO 8.1 | 0.5 | 0.25 | -0.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Quizzes%20-%20Project%201B%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20W5_1.pdf
2024-12-16 | Done | Python Retake part 2 | Take Python oral exam | Testing | ILO 0.2 | 0.16 | 0.16 | 0
2024-12-16 | Done | Read Chapter 9 | Introduction to unsupervised learning and understanding clustering basics. | Study | ILO 8.1 | 1.5 | 1 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Read Chapter 9 | Study of K-Means and DBSCAN clustering algorithms. | Study | ILO 8.1 | 2 | 1 | -1 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Read Chapter 9 | Exploration of Gaussian Mixture Models and density estimation. | Study | ILO 8.1 | 2 | 1 | -1 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Read Chapter 9 | Semi-supervised learning and label propagation techniques. | Study | ILO 8.1 | 2 | 1 | -1 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Hands-On%20Machine%20Learning%20with%20Scikit-Learn%2C%20Keras%20%26%20TensorFlow.pdf
2024-12-16 | Done | Review Chapter 9 | Read the Chapter 9 summary | Research | ILO 8.1 | 1 | 1 | 0
2024-12-16 | Done | Review Chapter 9 | Complete “ML-quiz-W5_2” in Brightspace | Testing | ILO 8.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Quizzes%20-%20Project%201B%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20W5_2.pdf
2024-12-17 | Done | Fill in WorkLog | Fill in WorkLog planning for Tuesday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-17 | Done | Stand-up meeting | Do the stand-up meeting with mentor group | Meeting | ILO 2.2 | 0.25 | 0.25 | 0
2024-12-17 | Done | Revising documents | Go through the WorkLog and fill in the "Task" column for previous weeks | Evidencing | ILO 1.2 | 1 | 0.5 | -0.5 |  | AAA
2024-12-17 | Done | Datalab tasks | Follow the k-means clustering tutorial | Study | ILO 8.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/K-Means-Clustering.ipynb
2024-12-17 | Done | Datalab tasks | Practice k-means clustering with practice notebook | Workshop | ILO 8.2 | 1 | 1.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/K-Means-Clustering.ipynb | Had a bit of a problem with VSC not seeing the environment or some of the packages on my new laptop.
2024-12-17 | Done | Datalab tasks | Implement k-means clustering in Python | Programming | ILO 8.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-12-17 | Done | Datalab tasks | Apply PCA for dimensionality reduction | Programming | ILO 8.2 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-12-17 | Done | Wednesday Math | Learn multivariable calculus | Study | ILO 8.1 | 3 | 1.5 | -1.5 |  | I understood the mathematical concept of multivariable calculus pretty quickly and so it didn't take as long as I predicted it to.
2024-12-17 | Done | Wednesday Math | Do the quiz about multivariable calculus | Testing | ILO 8.2 | 0.5 | 0.25 | -0.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/Quizzes%20-%20Project%201B%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20Multivariable%20Calculus.pdf | As stated above, I understood the concepts pretty quickly and did not have too much troubles with the quiz.
2024-12-17 | Done | Wednesday Math | Learn python for Symbolic calculus | Study | ILO 8.1 | 3 | 2.5 | -0.5
2024-12-20 | Done | Fill in WorkLog | Fill in WorkLog for Friday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-20 | Done | Stand-up meeting | Stand-up meeting with mentor group | Meeting | ILO 6.2 | 0.25 | 0.25 | 0
2024-12-20 | Done | Datalab Practice | Do the DBSCAN Jupyter notebook | Programming | ILO 8.1 | 1 | 3.25 | 2.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/DBSCN-clustering.ipynb | Had troubles with dependencies & packages
2024-12-20 | Done | Lecture | Informal DBSCAN Lecture | Lecture | ILO 8.1 | 0.25 | 0.25 | 0
2024-12-20 | Done | Datalab Practice | Read the DataCamp tutorials | Research | ILO 8.1 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/An%20Introduction%20to%20Hierarchical%20Clustering%20in%20Python%20_%20DataCamp.pdf
2024-12-20 | Done | Datalab Tasks | Implement Random Hierarchical Clustering | Programming | ILO 8.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-12-20 | Done | Datalab Tasks | Implement DBSCAN for Density-Based Clustering | Programming | ILO 8.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-12-20 | Done | Datalab Tasks | Evaluation and Model Comparison | Programming | ILO 8.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2024-12-20 | Done | Fill in WorkLog | Fill in WorkLog actual hours | Evidencing | ILO 1.2 | 0.25 | 0.15 | -0.1 |  | AAA
2024-12-20 | Done | Fill in Learning Log | Fill in Learning Log for week 5 | Evidencing | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-20 | Done | Fill in WorkLog | Evidence in WorkLog week 5 | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2024-12-20 | Done | Fill in Learning Log | Evidence in Learning Log week 5 | Evidencing | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
|  |  |  | Total Hours |  | 40.41 | 34.56 | -5.85
Week 6
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-06 | Done | Fill in WorkLog | Fill in WorkLog planning for Monday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-06 | Done | Fill in Learning Log | Fill in Learning Log for week 6 | Planning | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-06 | Done | Feature Engineering Learning | Learn how to apply feature engineering and selection | Study | ILO 6.2 | 1 | 1 | 0
06-07/01/2025 | Done | Feature Engineering Learning | Do DataCamp course "End-to-End Machine Learning" | Workshop | ILO 6.2 | 4 | 5.25 | 1.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/DataCamp%20-%20End-to-End%20Machine%20Learning.pdf | Due to sickness, combined with a few breaks due to me being busy, and this being done over 2 days, this took quite some time more than planned.
07&13.01.2025 | Done | Feature Engineering Learning | Do DataCamp course "Feature Engineering for Machine Learning in Python" | Workshop | ILO 6.2 | 4 | 5 | 1 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/DataCamp%20-%20Feature%20Engineering%20for%20Machine%20Learning%20in%20Python.pdf
2025-01-07 | Done | Lecture | Mathematics Lecture | Lecture | ILO 8.1 | 1.25 | 1.25 | 0
2025-01-07 | Done | Datalab Tasks | Do feature engineering | Programming | ILO 8.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-07 | Done | Datalab Tasks | Do feature selection | Programming | ILO 8.1 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-13 | Done | Learn Cross-Validation | Learn how to evaluate using Cross-Validation & its variants | Study | ILO 8.2 | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/dbf52b5262095348a7b3b20dff20823b21fc03fb/Block%20B/A%20Comprehensive%20Guide%20to%20K-Fold%20Cross%20Validation%20_%20DataCamp.pdf
2025-01-14 | Done | Learn Optimization Algorithms | Learn Gradient Descent Optimization Algorithm | Study | ILO 8.2 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/dbf52b5262095348a7b3b20dff20823b21fc03fb/Block%20B/Gradient%20Descent%20With%20Momentum%20from%20Scratch%20Program.ipynb
2025-01-14 | Done | Learn Optimization Algorithms | Learn Gradient Descent with Momentum | Study | ILO 8.2 | 1 | 1 | 0
2025-01-14 | Done | Learn Optimization Algorithms | Learn how to implement Regression Model | Study | ILO 8.1 | 1 | 1 | 0
2025-01-14 | Done | Learn Optimization Algorithms | Learn how to Train the Model with Gradient Descent | Study | ILO 8.1 | 1 | 2 | 1 |  | Slow work after a break during the datalab.
2025-01-14 | Done | Learn Optimization Algorithms | Do Assignment 1 | Programming | ILO 8.1 | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/AlgebraicExample_Final.ipynb | I had the material fresh in my head so I did it quite quickly.
14&17.01.2025 | Done | Learn Optimization Algorithms | Do Assignment 2 | Programming | ILO 8.1 | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/PricePred_temp.ipynb | Ran into an error, but after asking my mentor I continued on.
2025-01-19 | Done | Datalab tasks | Do the Linear Regression from Scratch | Programming | ILO 8.1 | 2 | 4 | 2 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/LinearRegression_Final.ipynb | I somehow missed this when catching up in week 7, so I did it later. Had a couple errors so the task took longer than expected.
2025-01-19 | Done | Fill in WorkLog | Evidence in WorkLog week 6 | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-19 | Done | Fill in Learning Log | Evidence in Learning Log week 6 | Evidencing | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
|  |  |  | Total Hours |  | 27.75 | 32.5 | 4.75
Week 7
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-13 | Done | Fill in WorkLog | Fill in WorkLog planning for Monday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-13 | Done | Fill in Learning Log | Fill in Learning Log for week 7 | Planning | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-13 | Done | Learn Fine Tuning | Learn about Model Fitting | Study | ILO 8.2 | 0.75 | 0.75 | 0
2025-01-13 | Done | Learn Fine Tuning | Learn about Hyperparameter Optimization Techniques | Study | ILO 8.2 | 0.5 | 0.5 | 0
2025-01-13 | Done | Organizing Documents | Move some documents over from old laptop to new laptop | Evidencing | ILO 1.2 | 0.5 | 0.5 | 0
2025-01-13 | Unplanned | Unplanned Incident | Get interrupted by a scam call | Distraction | ILO 1.2 | 0.1 | 0.1 | 0
2025-01-14 | Done | Fill in WorkLog | Fill in WorkLog for Tuesday | Planning | ILO 1.2 | 0.15 | 0.15 | 0 |  | AAA
2025-01-14 | Done | Stand-up meeting | Stand-up meeting with mentor group | Meeting | ILO 1.2 | 0.25 | 0.25 | 0
2025-01-14 | Done | Block A Evidencing | Fill out Block A Learning Log regarding Python Exam retake | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20A%20Retakes/Learning%20Log%20Y1A%20ADSAI%202024-2025%20(2).pptx
2025-01-16 | Done | Creative Brief Work | Apply Hyperparameter tuning | Programming | ILO 8.2 | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-16 | Done | Creative Brief Work | Analyse Errors | Debugging | ILO 8.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-17 | Done | Fill in WorkLog | Fill in WorkLog up to Friday | Planning | ILO 1.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-17 | Done | Stand-up meeting | Stand-up meeting with mentor group | Meeting | ILO 2.2 | 0.25 | 0.25 | 0
2025-01-17 | Done | Retake Evidencing | Complete Learning Log Block A | Evidencing | ILO 0.2 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20A%20Retakes/Learning%20Log%20Y1A%20ADSAI%202024-2025%20(2).pptx
2025-01-17 | Done | Datalab tasks | Read how to do logistical regression from scratch | Study | ILO 8.1 | 1 | 1 | 0
2025-01-17 | Done | Datalab tasks | Do logistical regression from scratch | Programming | ILO 8.2 | 4 | 5.75 | 1.75 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/LogisticRegression_Final.ipynb | Had a bunch of errors that took me some time to fix.
2025-01-18 | Done | Creative Brief Work | Do Datacamp course "Hyperparameter Tuning in Python" | Workshop | ILO 8.2 | 4 | 4.5 | 0.5 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20B/DataCamp%20-%20Hyperparameter%20Tuning%20in%20Python.pdf | Had a couple breaks while doing the course.
2025-01-19 | Done | Fill in Learning Log | Go through Learning Log section A and B to make sure they're done. | Evidencing | ILO 2.2 | 1 | 1 | 0 |  | AAA
2025-01-19 | Done | Fill in Learning Log | Evidence in Learning Log week 7 | Evidencing | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-19 | Done | Fill in WorkLog | Evidence in WorkLog week 7 | Evidencing | ILO 1.2 | 0.25 | 0.1 | -0.15 |  | AAA
|  |  |  | Total Hours |  | 18.5 | 20.6 | 2.1
Week 8
week plan: | - Weekplan item 1 - Weekplan item 2 - Weekplan item 3 - etc
Known Risks | [Enter known possible issues that are a risk for you to finish the high level week planning]
2025-01-20 | Done | Block A Evidencing | Finish Learning Log Block A | Evidencing | ILO 1.2 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/0e7620868343501c8dfcfa39189c1d60ae3a3b5e/Block%20A%20Retakes/Learning%20Log%20Y1A%20ADSAI%202024-2025%20(2).pptx
2025-01-20 | Done | Block A Evidencing | Hand in Block A retake | Evidencing | ILO 1.2 | 0.1 | 0.1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Block%20B/Submission%20History%20-%20Project%201A%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20(1).pdf
2025-01-20 | Done | Final Presentation | Begin work on presentation | Design | ILO 11.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Block%20B/Final%20Presentation.pptx
2025-01-20 | Done | Datalab tasks | Send e-mail regarding errors | Debugging | ILO 8.1 | 0.25 | 0.25 | 0
2025-01-20 | Done | Creative Brief Work | Work on Creative Brief | Programming | ILO 8.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-21 | Done | Fill in WorkLog | Fill in WorkLog for Monday & Tuesday | Planning | ILO 1.2 | 0.15 | 0.15 | 0 |  | AAA
2025-01-21 | Done | Stand-up meeting | Stand-up meeting with mentor group | Meeting | ILO 2.2 | 0.25 | 0.25 | 0
2025-01-21 | Done | Fill in Learning Log | Finishing touches to SMARTER-goals | Evidencing | ILO 2.2 | 0.25 | 0.25 | 0 |  | AAA
2025-01-21 | Done | Datalab tasks | Finish Jupyter notebooks Logistical & Linear Regression | Programming | ILO 8.1 | 4 | 4.25 | 0.25 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Block%20B/LogisticRegression_Final.ipynb | Had a couple of errors that I had to fix, which took time.
2025-01-21 | Done | Datalab tasks | Finish the Algebraic Example notebook | Programming | ILO 8.1 | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Block%20B/AlgebraicExample_Final.ipynb
2025-01-22 | Done | Creative Brief Work | Continue work on creative brief | Programming | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-22 | Done | Datalab tasks | Continue work on final report | Evidencing | ILO 11.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Deliverables/FinalReport_Maks_Burchard_240894.docx
2025-01-23 | Done | Datalab tasks | Do the SQL tasks | Programming | ILO 0.2 | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-23 | Done | Creative Brief Work | Finish creative brief | Programming | ILO 8.1 | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Deliverables/CreativeBrief_MaksBurchard_240894.ipynb
2025-01-23 | Done | Datalab tasks | Finish final report | Evidencing | ILO 11.1 | 4 | 4 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Deliverables/FinalReport_Maks_Burchard_240894.docx
2025-01-23 | Done | Block A Evidencing | Hand in Block A retake again with all documents, just to be sure | Evidencing | ILO 1.2 | 0.25 | 0.25 | 0 | https://github.com/BredaUniversityADSAI/2024-25b-fai1-adsai-MaksBurchard240894/blob/641210492f586c7e7048ca3999cc3dd4c452cfa2/Block%20B/Submission%20History%20-%20Project%201A%202024-2025%20-%20Breda%20University%20of%20Applied%20Sciences%20(1).pdf
2025-01-23 | Done | Fill in WorkLog | Finish WorkLog | Evidencing | ILO 1.2 | 1 | 1.1 | 0.1 |  | AAA
2025-01-23 | Done | Fill in Learning Log | Finish Learning Log section A and B | Evidencing | ILO 2.2 | 1 | 1 | 0
2025-01-23 | Planned | Fill in Learning Log | Finish Learning Log section C | Evidencing | ILO 2.2 | 1 |  | -1
2025-01-23 | Planned | Fill in Self-assesment rubric | Finish Self-assesment rubric | Evidencing | ILO 2.2 | 0.5 |  | -0.5
2025-01-23 | Planned | Final Presentation | Finish presentation | Design | ILO 11.1 | 2 |  | -2
|  | Max 4 hours tasks | [5 empty] | 0
|  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 27.25 | 24.1 | -3.15
[6 empty] | Total Hours | 251.69

## Overview (hidden)
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 0.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 3.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 4.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 7.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
ILO 11.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
If you add more rows to the Worklog Tasks and Time sheet, make sure to update the row count accordingly. For example, if you add an additional row for Week 1, you'll need to adjust all formula in Column C from H14 to H15 and F14 to F15 | bar: W1 to W4

## Drop-downs (hidden)
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 0.3
Unplanned | Meeting | ILO 1.5
Blocked | Programming | ILO 2.5
In-Progress | Research | ILO 3.5
Done | Testing | ILO 4.4
Delayed | Workshop | ILO 7.3
Cancelled | Planning | ILO 11.2
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break